## Feuil1
PhD GANTT CHART
PROJECT TITLE | Why different mines have different temperatures?
PROJECT MANAGER | Mylene Receveur
COMPANY NAME | University of Edinburgh
DATE | 2020-04-16
[6 empty] | Year 1 | [11 empty] | Year 2 | [11 empty] | Year 3 | [11 empty] | Year 4
TASK | TASK | START | DUE | DURATION | PCT OF TASK | Semester 1 |  |  |  | Semester 2 |  |  |  | Semester 3 |  |  |  | Semester 1 |  |  |  | Semester 2 |  |  |  | Semester 3 |  |  |  | Semester 1 |  |  |  | Semester 2 |  |  |  | Semester 3 |  |  |  | Semester 1 |  |  |  | Semester 2 |  |  |  | Semester 3
ID | TITLE | DATE | DATE | IN DAYS | COMPLETE | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D
1 | Part 1 : Heat recharge from BHE
1.1 | Literature review |  |  |  | 0%
1.1.1 | GSHP - BHE |  |  |  | 0%
1.1.2 | Solar heat flux |  |  |  | 0%
1,2 | 1D model |  |  |  | 0%
1,2,1 | Heat extraction profile |  |  |  | 0%
1,2,2 | Solar recharge |  |  |  | 0%
1,3 | 3D model |  |  |  | 0%
1,3,1, | Lateral recharge |  |  |  | 0%
1,3,2, | Footprint area |  |  |  | 0%
2 | Part 2 : Heat sources and temperature distribution in mines
2.1 | Literature review |  |  |  | 0%
2.1.1 | Modeling approaches |  |  |  | 0%
2.1.2 | Heat sources |  |  |  | 0%
2,1,2,1 | RHP |  |  |  | 0%
2,1,2,2 | Exothermic reactions |  |  |  | 0%
2,1,2,3 | Advective flow |  |  |  | 0%
2.2 | Benchmarks |  |  |  | 0%
2.3 | Modeling |  |  |  | 0%
2.3.1 | Temperature profile after mining and flooding |  |  |  | 0%
2.3.2 | Heat transfer mechanisms |  |  |  | 0%
2.3.3 | Coalfield geometry |  |  |  | 0%
2.3.4 | Mine geometry (residual void effects) |  |  |  | 0%
3 | Part 3 : Case study and Development of a predictive tool
3,1 | Literature review |  |  |  | 0%
3,1,1 | Geological context of the Midloothian and Dawdon-Horden Coalfileds |  |  |  | 0%
3,1,2, | Data selection |  |  |  | 0%
3,2 | Modeling |  |  |  | 0%
3,2,1, | Model set up |  |  |  | 0%
3,2,2, | Model validation |  |  |  | 0%
3,3 | Tool development |  |  |  | 0%
3,3,1 | Script compilation |  |  |  | 0%
3,1,2 | Test tools |  |  |  | 0%
4 | Thesis writing
4.1 | Understand heat sources in mines, transfer processes and heat recharge rate |  |  |  | 0%
4.2 | Footprint area and sustaibable heat production from mines |  |  |  | 0%
4.3 | Predict the geothermal potential and long term heat production from mines |  |  |  | 0%